# KELLY RESIDENCE

# Weekly Agenda

for the week of

6/9/26

Attendees: Toby Long, André Mandel, Chandra Baerg, Abby Wittman, Mai Thor

PDR / PRELIMINARY DESIGN REVIEW:

- Under review — June 9 board meeting, Schaffer’s Mill DRC

  - Fees paid — no action required from TLD unless DRC requests additional materials

STATE PERMIT PACKAGE (HCD/DAA):

- Target submittal June 26 — coordinating with Method Homes / John Bacon

  - 50% set issued — all consultants in coordination for state and local permit

MOD 1 INTERIORS:

- Coordinate Mod 1 interior layout to meet state permit deadline

  - Mechanical room, master bath, laundry scope to be finalized

CONSULTANT DELIVERABLES:

- All deliverables expected mid to late June for state and local permit

  - MEG: mech, plumbing, Title 24  ·  ISE: structural  ·  Triad Holmes: civil

LOCAL PERMIT — PLACER COUNTY:

- Target submittal July 12 — all digital plan check via permits.placer.ca.gov

  - 2025 CBC in effect January 1, 2026 — WUI / Part 7 mandatory

FDR PREPARATION:

- Target submittal July 29 — FDR board meeting August 11

  - Begin drawings after PDR approval and full consultant set received