# KELLY RESIDENCE

# Meeting Notes

Weekly Meeting

6/9/26

Attendees: Toby Long, André Mandel, Chandra Baerg, Abby Wittman, Mai Thor

# PDR / DRC STATUS:

- PDR submitted May 29 to Paul Ferro / Schaffer’s Mill DRC — package confirmed received

- DRC board meeting June 9 — PDR under review by board

- APN confirmed as 107-019-009 per Development Notebook — corrected on all sheets

- Building height corrected to 26’-4” on all elevation sheets

- Door and window schedules added to PDR package

- Paul Ferro to confirm rear setback in writing — 25’ lot-specific per Development Notebook

# STATE PERMIT (HCD/DAA):

- Method Homes PreCon Agreement executed 5/14/26 — $18,000 total (coordination, factory permit, reprographics)

- Target submittal June 26 — coordinate final package strategy with John Bacon / Keith Knutson

- Cedar soffit WUI compliance flagged — resolution required before FDR and permit submittal

- Mod 1 interior layout revision deferred until after PDR — begin next week

  - Mechanical room target 120–150 SF — currently undersized, expanding toward garage

  - Master bath layout, laundry, and dog run sightlines to be resolved

# MOD 1 INTERIORS:

- Vanity design to be developed and shared early next week — Mai, Chandra to lead

- Sally Kelly requested vanity / powder / makeup area at northeast corner

- Extra fireplace note in primary bedroom deleted

- Exterior doors: Toby prefers current inward swing — André to confirm whether single corner door suffices for privacy

- Kitchen window: 6’ wide slider preferred — countertop extension to exterior sill to be explored

- Operable windows both sides of bed, fixed panel across from entry hall

# DESIGN + STRUCTURAL:

- Module boundary revision confirmed: Mod 6 extended ~15 ft, Mod 5 shortened ~10 ft

- Optimizes rim beam for cantilevered deep front lower roof

- 6’ front eave within 14’-9” shipping width confirmed feasible

- Multi-ply LVL at outer module rims preferred — ISE to confirm sizing

- Double-height living space Mods 3/4/5/9/10 — team leaning all-modular, ISE coordinating

# CONSULTANT COORDINATION:

- Civil (Triad/Holmes / Petroni): utility trench routing from street to building absent from C2 — follow-up sent 6/1

- All other civil items confirmed on issued set: CAZ, snow storage 555 SF, hand-dug trenching, stormwater BMP

- Geotech (Reno Tahoe Geo / Timothy Miller): report expected within 2 weeks of early June

- Structural (ISE / Greg DeLeon): foundation and framing revisions in progress

- MEP (MEG): Cummings, Mathia, Hafner — all deliverables expected mid to late June

- Arborist (Arbor Solutions / James Piercy): tree report to be updated for FDR

- Landscape architect: Kalman Varga Design quoted ~$14,800 two-phase scope — decision deferred

# LOCAL PERMIT — PLACER COUNTY:

- Target submittal July 12 — all-digital via permits.placer.ca.gov

- 2025 CBC adopted January 1, 2026 — WUI / Part 7 mandatory on all sheets

- Modular foundation plan with marriage line callout required — coordinate with Method Homes and ISE

# FDR:

- Target submittal before end of July — FDR board meeting August 11

- FDR preparation begins after PDR approval and full consultant set receipt

- Progress set to be issued once consultant drafts received — target early next week for internal review