# KELLY RESIDENCE

# Meeting Recap

Client Weekly

6/16/26

Attendees: Toby Long, André Mandel, Chandra Baerg, Abby Wittman, Mai Thor

PDR / DRC STATUS:

- DRC board reviewed June 9 — PDR conditionally approved, minor corrections requested

  - Correction list received from Paul Ferro — TLD to respond within 10 days

- Rear setback written confirmation at 25’ lot-specific received from Paul Ferro

- Corrections underway: Chandra to issue revised sheets this week

STATE PERMIT (HCD/DAA):

- Target submittal June 26 — 10 days out, package 80% assembled

- Method Homes / John Bacon: factory permit strategy call completed

- WUI cedar soffit: resolution confirmed — spec revised to non-combustible alternate

- Mod 1 interior layout revision in progress — mechanical room expanded, master bath revised

- ISE structural revisions incorporated into permit set

MOD 1 INTERIORS:

- Vanity design developed and shared with Kellys — northeast corner layout per Sally’s request

- Feedback expected from Roland and Sally by end of week

- Mechanical room: 128 SF achieved with Mod 1 expansion toward garage

- Master bath WC sightline resolved — partition wall repositioned

- Kitchen window: 6’ slider confirmed — countertop extension to sill detail added

CONSULTANT COORDINATION:

- Geotech (Reno Tahoe Geo / Timothy Miller): report received — no adverse findings

  - Bearing capacity confirmed — conventional stem wall foundation viable

- Civil (Triad/Holmes / Petroni): utility trench routing added to C2 — outstanding item closed

- Structural (ISE / DeLeon): LVL sizing confirmed at outer module rims, Mod 3/4/5 all-modular confirmed

- MEP (MEG): mechanical and plumbing drafts received — TLD review underway

- Arborist (Arbor Solutions / Piercy): updated tree report to be ordered for FDR

LOCAL PERMIT — PLACER COUNTY:

- Target submittal July 12 — all-digital via permits.placer.ca.gov

- Foundation plan with marriage line callout: ISE and Method Homes coordinating

- WUI / Part 7 compliance sheet to be added to permit set

FDR:

- FDR prep begins following state permit submittal June 26

- FDR submittal target July 29 — FDR board August 11

- Landscape architect selection: recommend decision by July 1 to allow FDR inclusion

- Kalman Varga Design quote ($14,800 two-phase) on hold pending owner direction